## Sheet1
id | Task | Start | End | Duration
1 | Table and electrical box building | 2021-03-12 | 2021-03-25 | 10
2 | Hardware final design, buttons, Leds and components tests | 2021-03-15 | 2021-03-16 | 2
3 | Sigle components tests (printer, scale, LEDs and buttons) with scripts | 2021-03-17 | 2021-03-23 | 5
4 | Components, box and table assembling | 2021-03-26 | 2021-04-01 | 5
5 | Integration and tests of system | 2021-03-24 | 2021-04-01 | 7
Formulas:
Duration = NETWORKDAYS([Start],[End])